## Planning
- |  | Game: | Vendetta
|  | Team Members: | Marta Stąporek
Kamil Boksa
| Task category | Task name | Task description | Difficulty level [1-3] | Assigned to | Progress [none ¦ in progress ¦ done] | End date
1 | Must have | Game board | Should contain 2 areas | 1 | Kamil | done | 4.09
2 |  | Character creation | @ as character, 3 classes available | 2 | Marta | done | 5.09
3 |  | Movement | Character should move when W,A,S,D used | 1 | Kamil | done | 5.09
4 |  | Hall of fame | Name, max level, time spent, monsters killed etc. | 3 | Kamil | done | 7.09
5 |  | Game intro, about and credits | Short story as introduction | 1 | Marta | done | 5.09
6 |  | Hero statisctics | Experience, Strenght, Lifes | 2 | Kamil | done | 6.09
7 |  | Win / lose screen | Show win or lose screen when game finished | 1 | Marta | done | 5.09
8 |  | Inventory | Collect items. Show item name, count, weight, type and total weight. | 3 | Kamil | done | 6.09
9 |  | Colours | colored maps and boss | 2 | Marta | done | 7.09
10 |  | 1st map challenge | Simple fight | 1 | Kamil | done | 7.09
11 |  | Boss fight | Hot, warm, cold | 2 | Marta | done | 7.09
1 | Should have
2
3
4
5
6
1 | Nice to have | More levels | Create more than 2 areas, with different enviroment and difficulty level | 3 | Marta / Kamil | none
2 |  | More races | for example, dwarves, elfs, etc. | 2 | Marta / Kamil | none
3 |  | Random class and race pick | picks randomly players class and race | 2 | Marta / Kamil | none
4 |  | Moving enemies | Enemies moving randomly around the map | 3 | Marta / Kamil | none
5
6